## 9ShotsStudion
| 9Shot Studio | 2016-03-21
Sl. No. | Module | Man Days
1 | Low Level Design (Milestone 1) | 13
2 | UI Design
| Home Page | 2
| Details Page | 2
| Package Page | 1
3 | HTML Full Prototype - Responsive | 7
3 | Documentation (SRS) | 1
4 | Development & Testing (Milestone 2) | 10
5 | Creating Developemt Environment PHP | 0
6 | Admin
| Manage clients | 1
7 | Manage Categories | 0.5
8 | Manage Youtube video links | 1
9 | Manage Images | 1
10 | Manage Packages | 1
12 | Front end
13 | Home page content listing | 1
14 | Details Page content listing | 0.5
15 | Package page | 0.5
19 | Code Review | 0.5
19 | Testing and Fixes
20 | Internal Testing (Cycle 1) | 2
21 | Bug Fixes (Cycle 1) and release | 1
22 | UAT Support & Implementation | 0
23 | Project Management | 1
24 | TOTAL | 24
Out of scope
Data entry
Assumption
Package page is just package listing page
Videos will be embed from youtube, Images will be stored in site
No Other Documents

## Server Details
Minimum Server Requirement
Server Type | Linux
Hosting Type | Shared
Minimum Space | 2 GB
Minimum RAM | 512 MB